TO:	HPD Operations Leadership

FROM:	Pranish Pradhan

DATE:	August 25, 2026

RE:	Prioritization pilot for GENERAL and PAINT/PLASTER complaint resolution

DECISION REQUESTED:	Approve a limited prioritization pilot and staged timestamp-tracking rollout, subject to establishing a broader continuous baseline before measuring results.

NOTE:	Independent portfolio analysis using public NYC 311 HPD data; not an official HPD work product.

The problem

Two complaint categories stand out as leading contributors to delay in this dataset - not necessarily the majority of it, since the total excess days across every category haven't been summed here, but the largest pairing observed. GENERAL runs past the 30-day mark used in this analysis less often than PAINT/PLASTER (5 of 22 valid closed tickets, about 23%), but when it does, it runs long - about 85 days over on average. PAINT/PLASTER crosses that mark more often (15 of 43 tickets, about 35%) and carries the single largest total excess-day burden of any category, 507 days. Together, these two categories account for 933 excess days, more than any other pairing in the data.

The 30-day mark is a threshold chosen for this analysis, not a documented HPD service-level agreement - worth stating plainly, since the recommendation below leans on it.

What's being proposed

A one-quarter pilot that prioritizes existing inspection and repair-coordination capacity toward GENERAL and PAINT/PLASTER, paired with a staged rollout of timestamp tracking at three points in the process that currently go unrecorded: when a ticket is routed to a crew, when repair work starts, and when it's finished.

This is deliberately not a request to reallocate staff outright. The data shows which categories are slow; it says nothing about staffing levels, workload, or cost, so it can't by itself prove a staffing shortfall is the cause. The pilot is how that gets tested before anyone commits to a permanent change or a headcount request.

Tracking rolls out the same way: piloted with the crews already working these two categories, then extended once the data-entry approach is checked for quality and usability. Other categories are watched during the pilot as a point of reference, not as a formal control group - they may differ in volume and workload, so the comparison is informative, not conclusive.

How the pilot runs

- Owner - HPD operations lead for inspection and repair-crew scheduling, working with the HPD data/reporting lead responsible for implementing the timestamp fields.

- Length - one quarter, or until at least 30 valid tickets per category have come through, whichever takes longer. That count is an operational minimum for a readable comparison, not a statistically validated sample size.

- Scope - GENERAL and PAINT/PLASTER only.

- Baseline - before the pilot starts, pull a continuous quarter (or more) of prior resolution data for these two categories, rather than relying only on the narrow 3-day sample this report is built on. That continuous pull becomes the actual number the pilot is measured against.

- Comparison - pilot-period numbers for these two categories against that continuous baseline, while watching the rest for any side effects.

What the numbers could look like

No pilot has run yet, so this is a range built on assumptions, not a measured result. Baseline: 933 combined excess days for GENERAL and PAINT/PLASTER from this report's narrow sample; the pilot itself will be measured against the continuous baseline described above.

| Scenario | What would have to be true | Excess days recovered |
| --- | --- | --- |
| Conservative | Prioritization only partly holds against existing workload | ~140 days (15%) |
| Base case | Pilot runs as scoped, full quarter, both categories | ~280 days (30%) |
| Optimistic | Early pilot results prompt a process fix mid-quarter | ~467 days (50%) |

What counts as working

At the end-of-quarter review, the pilot is worth expanding if all of the following hold:

- at least 30 valid tickets per category came through during the pilot.

- excess days for the two categories dropped at least 15% against the continuous baseline described above.

- no other category's median resolution time increased by more than 10% over the same stretch.

- timestamp entries are at least 95% complete for participating tickets.

What could go wrong

- Displacement - fixing two categories could slow others. Watched for directly during the pilot via median resolution time, not just assumed away.

- Thin baseline - the historical numbers above come from a narrow 3-day window in the source data, all within the same single hour each day - not a full month, despite how that might read at a glance. Any wider rollout decision should wait on a broader, continuous pull of data first.

- Pushback on tracking - new data-entry steps are an easy thing for crews to skip or half-fill. Starting with a small group first, before expecting it everywhere, is the point of the staged rollout.

Where this comes from, and its limits

Built on 405 valid closed tickets, all from a 3-day window in April 2024, all created within the same hour each day - a narrow slice, not a representative month. Assumes ticket volume and mix stay roughly where they were in that window; a real shift in complaint patterns would move the baseline. Doesn't account for things outside the data - contractor availability, weather, budget cycles - that could affect timing regardless of anything proposed here. The 15/30/50% figures are a chosen range meant to bound a realistic outcome, not numbers pulled from an actual trial.

Bottom line

If the pilot performs at even the cautious end of this range, it will represent a meaningful reduction in how long tenants wait on two of the worst-performing categories in the data - but that's a modeled projection to justify running the pilot, not a result to promise up front. The tracking piece matters more in the long run than any single quarter's number: it's what turns "this category is slow" into "this is where, specifically, it's slow" - which this analysis, as it stands, can't yet answer.